## Document Control
C&F Agent Interface - Delivery Planning Register
Field | Value
Client | Shree Cement / Bangur
Document reference | CNF-API-PLAN-001
Version | 1.2
Date | 2026-07-30
Prepared by | SAP Backend Integration Team
Scope | Delivery timeline plus supporting registers: business rules, effort, validation, source of record, assumptions
Companion objects | CNF_API_Classification.xlsx / CNF_API_CLASSIFICATION.pdf (the API list itself)
BASIS OF PREPARATION
Item | Status
SAP system access | Not yet granted
Business sign-off on process rules | Not obtained
The Timeline sheet dates the delivery plan from today and shows how development-access delay converts into
go-live slip. Effort figures are pre-access ranges. The validation register is the substance of the access
request: each item converts an estimate into a verified fact.
SHEET GUIDE
Timeline | COMPRESSED schedule: all ten APIs built by 09 Oct 2026, UAT-ready 28 Oct 2026. Includes the conditions the dates depend on, risks accepted, and a descope option
Business Rules | Functional constraints, derivations and reliability rules per API
Effort | Indicative pre-access ranges, including the Document Compliance contingency
Validation Register | The 29 checks requiring system access
Source of Record | Cross-system ownership: S/4HANA, Commerce Cloud T1/T2, Datasphere
Assumptions | Eleven stated assumptions and the impact if each proves wrong

## Timeline
DELIVERY TIMELINE - COMPRESSED PLAN
Anchored to Thu 30 Jul 2026. Target: all ten APIs built within two months of access, UAT-ready within three months of today. Working days exclude weekends; public holidays not deducted. THIS SCHEDULE IS CONDITIONAL - see Part C.
PART A - WORK IN PROGRESS NOW (no system access required)
Ref | Activity | Start | Finish | Working days | Status
P0 | API classification and standard-versus-custom analysis | Thu 30 Jul 2026 | Mon 03 Aug 2026 | 3 | COMPLETE
P0 | Functional and technical specification, ten APIs | Thu 30 Jul 2026 | Tue 04 Aug 2026 | 4 | COMPLETE
P0 | Cross-system source-of-record model | Mon 03 Aug 2026 | Tue 04 Aug 2026 | 2 | COMPLETE
P0 | Validation register - the 29 access-dependent checks | Mon 03 Aug 2026 | Tue 04 Aug 2026 | 2 | COMPLETE
P0 | OData contract and type-discipline standard | Wed 05 Aug 2026 | Fri 07 Aug 2026 | 3 | In progress
P0 | Idempotency and correlation design | Wed 05 Aug 2026 | Fri 07 Aug 2026 | 3 | In progress
P0 | Service decomposition and package layout proposal | Fri 07 Aug 2026 | Mon 10 Aug 2026 | 2 | In progress
P0 | Development conventions proposal for both ABAP developers | Mon 10 Aug 2026 | Tue 11 Aug 2026 | 2 | Planned
P0 | Master-data knowledge-transfer intake instrument | Mon 10 Aug 2026 | Wed 12 Aug 2026 | 3 | Planned
PART A CONCLUSION | Pre-access design is largely complete and fully exhausted by mid-August. Because that design work is already done, Part B foundations can begin on day one of access rather than after a ramp-up. That is the first source of compression.
PART B - COMPRESSED BUILD (assumes DEV access granted Mon 10 Aug 2026)
Phase | Workstream | APIs | Start | Finish | Working days | Resourcing | Exit deliverable
P1 | Validation sprint | All ten | Mon 10 Aug 2026 | Wed 12 Aug 2026 | 3 | ABAP lead, Basis, Tax | V-01, V-02, V-05, V-06, V-15, V-16, V-21, V-23 closed in three days. Requires Basis and Tax pre-booked before day one
P2 | Shared foundations | Cross-cutting | Mon 10 Aug 2026 | Fri 21 Aug 2026 | 10 | ABAP x2 | Idempotency store, correlation and logging, error contract, authorization, conversion utilities. Design already complete pre-access, so build starts on day one
P3 | Track A - reads | API-04, API-01 | Mon 17 Aug 2026 | Fri 04 Sep 2026 | 15 | ABAP x1-2 | Stock Availability and Check MIGO live through Integration Suite
P4 | Track B - delivery and receipt | API-10, API-03, API-02 | Mon 24 Aug 2026 | Wed 16 Sep 2026 | 18 | ABAP x1-2 | Modify DI, Create DI, Submit MIGO. Write pattern proven and reused
P5 | Track C - dispatch and billing | API-05, API-06 | Thu 27 Aug 2026 | Fri 09 Oct 2026 | 32 | ABAP x2 dedicated | Shipment Cost estimate and Invoice Creation orchestration. Long pole - needs its own resourcing from day fourteen
P6 | Track D - correction and statutory | API-07, API-08, API-09 | Fri 18 Sep 2026 | Fri 09 Oct 2026 | 16 | ABAP x1, Tax | Invoice Correction, E-Invoice Correction, E-Way Bill Extension
P7 | Continuous integration testing | All ten, rolling | Fri 04 Sep 2026 | Fri 23 Oct 2026 | 36 | ABAP, CPI, Commerce | Joint testing runs alongside build from week four rather than as a trailing phase. Requires CPI and Commerce availability throughout
P8 | Stabilisation and UAT handover | All ten | Mon 12 Oct 2026 | Wed 28 Oct 2026 | 13 | ABAP x2, CPI, Commerce | Concurrency and negative cases, reconciliation paths, defect burn-down
MILESTONE | Date | From access | From today | Meaning
G1 - Classification verified | Wed 12 Aug 2026 | 3 working days |  | Standard-versus-custom confirmed against the real system. Licensing answered. Effort ranges collapse
G2 - First endpoints live | Fri 04 Sep 2026 | 20 working days |  | Stock Availability and Check MIGO proven end to end at zero business-state risk
G3 - Write pattern proven | Wed 16 Sep 2026 | 28 working days |  | Delivery and receipt commands posting with idempotency
G4 - ALL TEN APIs BUILT | Fri 09 Oct 2026 | 44 working days |  | API formulation complete - approximately 2 months from access
G5 - Ready for QAS and UAT | Wed 28 Oct 2026 | 57 working days | 64 working days | Stabilised and handed over - approximately 11.4 weeks from access
PART C - WHAT BUYS THE COMPRESSION (conditions, not optimism)
Ref | Condition required | Why it compresses | If not met
C-1 | Three ABAP developers, not two, from day fourteen | Track C (Invoice Creation and Shipment Cost) runs in parallel with Tracks B and D instead of after them. This is the single largest lever | Add four to five weeks. Two developers cannot parallelise P5 against P4 and P6
C-2 | Basis and Tax pre-booked before day one | Validation sprint closes in three days instead of a week. Landscape, licensing and authorization answered immediately | Add one week, and every downstream track starts late
C-3 | Document Compliance licensing (V-02) confirmed on or before day one | API-08 and API-09 stay near-standard wrappers | Add four to five weeks combined. Both APIs become bespoke statutory clients
C-4 | Invoice synchronicity (V-04) and delivery predecessor (V-05) answered in week one | Track C starts on day fourteen with a settled design instead of waiting | Track C cannot start. Direct one-for-one slip on the critical path
C-5 | Master-data knowledge transfer (V-12) delivered in weeks one and two | Field mapping proceeds alongside build rather than blocking it | Payload correctness becomes a UAT discovery rather than a build input. Rework risk on every API
C-6 | CPI and Commerce available for joint testing from week four | Testing runs continuously alongside build instead of as a trailing fifteen-day phase | Testing reverts to a trailing phase. Add two to three weeks
C-7 | Commerce-to-SAP mapping ownership (V-27) decided in week one | SAP APIs receive settled organisational values instead of provisional ones | Rework across API-01 to API-06 when the mapping is finally agreed
PART D - RISKS ACCEPTED BY COMPRESSING
Risk | Consequence
Float is removed | The original plan carried buffer between phases. This one does not. Any single blocker consumes schedule directly rather than absorbing into slack
The highest-risk item gets the least slack | Invoice Creation orchestration is the hardest engineering in the inventory and is now on the critical path with no contingency
Defects surface later | Testing overlaps build rather than following it. Issues found in week eight are cheaper than week twelve, but a systemic design fault found late has nowhere to go
Key-person dependency | With three developers on four parallel tracks, one person's absence for a week is a schedule event, not an inconvenience
No quality-client gate | The two-system landscape (V-15) removes a QAS staging step. That helps this schedule and hurts release confidence, on APIs that post financial documents
PART E - IF THE CONDITIONS ARE NOT MET
Scenario | All ten APIs built | UAT-ready | Comment
Compressed plan, all conditions met | Fri 09 Oct 2026 | Wed 28 Oct 2026 | Target scenario. Requires C-1 to C-7
Two ABAP developers instead of three | Tue 10 Nov 2026 | Fri 27 Nov 2026 | Track C serialises behind Tracks B and D
Document Compliance not licensed | Tue 10 Nov 2026 | Fri 27 Nov 2026 | API-08 and API-09 become bespoke statutory builds
DESCOPE OPTION - HITS THE DATE WITH TWO DEVELOPERS
Defer | Effect | Rationale
API-05 Shipment Cost - ESTIMATE mode only | Removes twelve to eighteen days from Track C | ACTUAL mode (posted cost read) is standard and ships on plan. The pre-document estimate is the new-construction half and has no standard counterpart. Portal can display posted cost first and add the pre-commitment estimate in a second drop
API-10 Modify DI | Removes four to six days from Track B | Already flagged as our proposed addition, absent from the client process register. If it is genuinely out of scope (V-25), it costs nothing to drop
COMBINED EFFECT | All ten less the two deferred items land approximately Wed 14 Oct 2026 with TWO developers |  | This is the realistic path if a third ABAP resource cannot be found
COST OF DELAY - ACCESS REMAINS THE ONLY HARD DEPENDENCY
If DEV access is granted | All ten APIs built | UAT-ready | Slip
Mon 10 Aug 2026 (plan) | Fri 09 Oct 2026 | Wed 28 Oct 2026 | -
Mon 17 Aug 2026 (+1 wk) | Fri 16 Oct 2026 | Wed 04 Nov 2026 | 5 working days
Mon 24 Aug 2026 (+2 wk) | Fri 23 Oct 2026 | Wed 11 Nov 2026 | 10 working days
Mon 07 Sep 2026 (+4 wk) | Fri 06 Nov 2026 | Wed 25 Nov 2026 | 20 working days
NOTE | This compressed schedule is achievable but it is not a forecast - it is a commitment conditional on Part C. The honest position to state is: we can hit these dates if C-1 to C-7 hold, and here is precisely what moves if they do not. Access remains the sole predecessor of every phase in Part B.

## Business Rules
FUNCTIONAL BUSINESS RULES
Rule | API | Rule statement | Type | Status
BR-01.1 | API-01 Check MIGO | Receipt status must distinguish Pending / Partial / Complete. A binary indicator is insufficient - partial truck receipts are normal in depot replenishment. | Constraint | Proposed
BR-01.2 | API-01 Check MIGO | Pending quantity equals ordered quantity less cumulative received quantity, derived from document flow, not stored. | Derivation | Proposed
BR-01.3 | API-01 Check MIGO | Results restricted to plants the user is authorized for. | Security | Proposed
BR-02.1 | API-02 Submit MIGO | Receipt quantity must not exceed pending quantity. | Constraint | Proposed
BR-02.2 | API-02 Submit MIGO | Partial receipt permitted; residual remains pending. | Constraint | Proposed
BR-02.3 | API-02 Submit MIGO | Posting is rejected in full if any line fails. No partial commit. | Reliability | Proposed
BR-02.4 | API-02 Submit MIGO | A repeated call carrying an already-processed request identifier returns the original result and does not post again. | Reliability | Proposed
BR-03.1 | API-03 Create DI | Delivery quantity must not exceed open source quantity. | Constraint | Proposed
BR-03.2 | API-03 Create DI | Exactly one storage location applies per delivery, held at header level. Multiple batches may be allocated within it. | Constraint | Proposed
BR-03.3 | API-03 Create DI | Allocated batch quantities must sum exactly to the delivery quantity. Neither under- nor over-allocation is permitted. | Constraint | Proposed
BR-03.4 | API-03 Create DI | Driver mobile is mandatory where dispatch documents are issued by SMS. | Constraint | Proposed
BR-03.5 | API-03 Create DI | Creation is atomic: delivery and its logistics attributes commit together or not at all. | Reliability | Proposed
BR-04.1 | API-04 Stock Availability | Only storage locations belonging to the requested plant are returned. | Constraint | Proposed
BR-04.2 | API-04 Stock Availability | Only unrestricted stock is allocatable. Blocked and quality-inspection stock is displayed but flagged not allocatable. | Constraint | Proposed
BR-04.3 | API-04 Stock Availability | Allocation rank derived by ascending manufacture date where batch age governs issue sequence. Whether SAP determines this or the portal proposes it is unresolved - see V-08. | Open | Query
BR-04.4 | API-04 Stock Availability | Where shelf life applies, batches past expiry are excluded from the allocatable set and reported separately. | Constraint | Proposed
BR-04.5 | API-04 Stock Availability | Quantities returned in base unit of measure with the unit stated explicitly. No silent conversion. | Constraint | Proposed
BR-04.6 | API-04 Stock Availability | The response is a point-in-time read. It carries no reservation and confers no guarantee stock remains available at posting. | Constraint | Proposed
BR-05.1 | API-05 Shipment Cost | The estimate is non-binding and creates no SAP document. No shipment, no cost document, no number-range consumption. | Constraint | Proposed
BR-05.2 | API-05 Shipment Cost | Where no freight rate is maintained for the route and transporter, the API returns an explicit no-rate condition. It must NEVER return zero cost, which the portal would render as free carriage. | Constraint | Proposed
BR-05.3 | API-05 Shipment Cost | Incoterm governs whether the estimate is chargeable to the customer or absorbed. The two cases must be distinguishable in the response. | Derivation | Proposed
BR-05.4 | API-05 Shipment Cost | Estimated and actual cost must be separately identifiable throughout. An estimate is never presented as a posted cost. | Constraint | Proposed
BR-05.5 | API-05 Shipment Cost | Mode ACTUAL is read-only. Cost correction is a separate process, not in this API. | Constraint | Proposed
BR-06.1 | API-06 Invoice Creation | Stages execute in sequence. Each stage precondition is successful completion of its predecessor. | Constraint | Proposed
BR-06.2 | API-06 Invoice Creation | The sequence is NOT a single unit of work. A failure at stage n does not and must not roll back stages 1 to n-1, which are already committed and, for goods issue, have moved physical stock. | Reliability | Proposed
BR-06.3 | API-06 Invoice Creation | The process must be resumable. A failed stage is retried from that stage, not from the beginning. Retrying must never repeat a completed stage. | Reliability | Proposed
BR-06.4 | API-06 Invoice Creation | Partial completion is reported explicitly, never concealed. The portal must render for example goods issue posted / billing failed as a distinct actionable state. | Reliability | Proposed
BR-06.5 | API-06 Invoice Creation | Idempotent at both levels: a repeated call with a known request identifier returns current state without re-executing; each stage is individually guarded. | Reliability | Proposed
BR-06.6 | API-06 Invoice Creation | Every stage records its correlation identifier and resulting document key for reconciliation. | Reliability | Proposed
BR-06.7 | API-06 Invoice Creation | Synchronous completion versus immediate return with a process identifier is an architectural decision - see V-04. This specification assumes immediate return, because BR-06.2 makes reliable synchronous completion unachievable across six stages including two external calls. | Open | Decision required
BR-07.1 | API-07 Invoice Correction | Correction and reversal are distinct SAP processes and must not share one code path. | Constraint | Proposed
BR-07.2 | API-07 Invoice Correction | Corrections are made by a new correcting document referencing the original. The original is never altered. | Constraint | Proposed
BR-07.3 | API-07 Invoice Correction | Where the original carries a statutory invoice reference, the correction must first evaluate the e-invoice position through API-08 before any billing action. | Constraint | Proposed
BR-08.1 | API-08 E-Invoice Correction | A generated IRN cannot be amended. Correction is cancel-and-reissue within the statutory window only. | Constraint | Proposed
BR-08.2 | API-08 E-Invoice Correction | Inside the statutory cancellation window the API cancels the IRN and reissues. Outside it, the API must refuse cancellation and route the correction to a credit or debit note instead. | Constraint | Proposed
BR-08.3 | API-08 E-Invoice Correction | Cancellation is blocked where an active E-Way Bill is linked to the invoice. The E-Way Bill position must be evaluated first. | Constraint | Proposed
BR-08.4 | API-08 E-Invoice Correction | The statutory window is evaluated server-side from the IRN generation timestamp, never from a client-supplied value. | Security | Proposed
BR-08.5 | API-08 E-Invoice Correction | Every cancellation and reissue attempt is recorded with its statutory response for audit, successful or failed. | Reliability | Proposed
BR-08.6 | API-08 E-Invoice Correction | The exact statutory window duration and its edge behaviour must be confirmed against current regulation and the installed component - see V-14. | Open | Query
BR-09.1 | API-09 E-Way Bill Extension | Transport mode is Road only. No mode parameter is exposed. | Constraint | Proposed
BR-09.2 | API-09 E-Way Bill Extension | Extension period is 24 hours and may be repeated. | Constraint | Proposed
BR-09.3 | API-09 E-Way Bill Extension | Vehicle change is a Part B update, not an extension. The two must not be conflated. | Constraint | Proposed
BR-09.4 | API-09 E-Way Bill Extension | Every attempt, successful or failed, is recorded with its statutory response for audit. | Reliability | Proposed
BR-09.5 | API-09 E-Way Bill Extension | Reason codes must match the current statutory code list - see V-13. | Open | Query
BR-10.1 | API-10 Modify DI | Modification rejected once goods issue is posted. | Constraint | Proposed
BR-10.2 | API-10 Modify DI | Editable field scope requires confirmation - see V-11. | Open | Decision required
BR-10.3 | API-10 Modify DI | Revised quantity remains subject to BR-03.1 and BR-03.3. | Constraint | Proposed

## Effort
INDICATIVE EFFORT - PRE-ACCESS RANGES
Ranges will move once the Validation Register is closed. Stated to support sequencing, not to fix a schedule.
Item | Class | Low (days) | High (days) | Notes
Cross-cutting foundations | - | 15 | 20 | Idempotency, correlation and logging, error contract, authorization, type discipline. No standard SAP equivalent for idempotency.
API-01 Check MIGO | C | 8 | 12 | Composite read
API-02 Submit MIGO | S | 5 | 8 | Standard posting plus integration scaffolding
API-03 Create DI | S | 6 | 10 | Standard creation plus logistics attributes
API-04 Stock Availability | C | 8 | 12 | Composite read with allocation ranking
API-05 Shipment Cost | X / S | 12 | 18 | Pre-document estimate is new construction
API-06 Invoice Creation | X | 25 | 35 | Orchestration and state model - highest risk item
API-07 Invoice Correction | S | 5 | 8 | Standard documents plus statutory guard
API-08 E-Invoice Correction | S | 6 | 10 | Assumes Document Compliance licensed; window and branch logic
API-09 E-Way Bill Extension - standard route | S | 3 | 5 | Assumes Document Compliance licensed and configured
API-10 Modify DI | S | 4 | 6 | Standard change. Proposed addition, not in the client register
INDICATIVE TOTAL (Document Compliance available) |  | 97 | 144 | Excludes functional analysis, integration-layer work, testing cycles and defect resolution
API-09 E-Way Bill Extension - custom route | X | 15 | 20 | If Document Compliance is NOT available. Variance against the standard route is 12-15 days.
API-08 E-Invoice Correction - custom route | X | 14 | 20 | If Document Compliance is NOT available. Requires a bespoke statutory client and status store.
CONTINGENCY IF NO DOCUMENT COMPLIANCE |  | +20 | +25 | Combined additional effort for API-08 and API-09 on the custom route. This is why V-02 is ranked Critical.

## Validation Register
VALIDATION REGISTER - THE DEVELOPMENT ACCESS REQUEST
Each item is a specific check that converts an estimate in this proposal into a verified fact. Ranked by how much of the inventory it gates.
Ref | Validation required | Method | Gates | Priority | Owner | Status
V-01 | Backend product and exact release / component levels. Which released APIs and CDS views are available and permitted. | System status; released-object inspection | ALL TEN - determines whether several APIs need custom construction at all | Critical | Basis / ABAP | Open
V-02 | Is SAP Document Compliance for India licensed, installed and configured? Which statutory actions are delivered - IRN generate, IRN cancel, E-Way Part B, E-Way extension? | Component and configuration inspection | API-08, API-09, API-06 statutory stages. Largest single effect on the estimate | Critical | Basis / Tax | Open
V-03 | Integration Suite is confirmed in the runtime path. Does it own the outbound statutory calls and their credentials, or is ABAP expected to call the statutory service directly? | Architecture confirmation | API-08, API-09, NFR-07 | Critical | Architect | Open
V-04 | Is the dispatch-to-invoice sequence a single synchronous command or a staged process? | Functional and architecture decision | API-06 entirely, API-05 | Critical | SD / Architect | Open
V-05 | Is the source demand document for a delivery a sales order or a stock transport order? Does this differ by business scenario? | Document-chain trace | API-03, API-10, API-01 | Critical | SD | Open
V-06 | Which transport solution is in use - classic shipment and shipment costing, or an alternative? | Configuration inspection | API-05 both modes, API-06 shipment stages | High | SD / LE | Open
V-07 | What does available stock mean operationally - unrestricted physical, availability-check result, or batch-eligible? | Functional decision | API-04, API-03 | High | MM / Business | Open
V-08 | Is batch issue sequence determined by SAP configuration or proposed by the portal? | Configuration inspection and functional decision | API-04, API-03 | High | MM / SD | Open
V-09 | MRN is a Datasphere object. What links it to the SAP material document, and does the portal require it echoed through SAP at all? | Functional confirmation | API-01, API-02 | High | MM / Datasphere | Open
V-10 | Do route, freight condition and rate configuration support pricing simulation without document creation? | Configuration inspection | API-05 ESTIMATE mode | High | SD / LE | Open
V-11 | Which delivery fields are editable after creation, and until which status? | Functional decision | API-10 | High | SD | Open
V-12 | Master and reference code dictionaries: brand and grade derivation, material grouping, business segment, organisational codes, Incoterm treatment. | Knowledge transfer and configuration inspection | EVERY PAYLOAD FIELD ACROSS ALL TEN | Critical | SD / Business master data | Open
V-13 | Current statutory reason-code list for E-Way Bill extension. | Statutory and configuration confirmation | API-09 | Medium | Tax | Open
V-14 | Statutory cancellation window for e-invoice, its edge behaviour, and E-Way Bill linkage rules on cancellation. | Functional and statutory confirmation | API-08, API-07, API-06 | High | Tax / SD | Open
V-15 | Landscape: development, quality and production clients, and the transport route. | Basis confirmation | ALL - a two-client route with no quality client is not appropriate for APIs with financial impact | Critical | Basis | Open
V-16 | Gateway topology: embedded or hub. Service registration and activation process. | Basis confirmation | ALL | Critical | Basis | Open
V-17 | Package, namespace, message class, exception and transport conventions. | Development standards agreement | ALL - must be agreed before either developer writes a class | High | ABAP lead | Open
V-18 | Approved error schema and HTTP status mapping across the landscape. | Integration architecture decision | NFR-03, all | High | Architect | Open
V-19 | Correlation and logging standard end to end. | Integration architecture decision | NFR-02, all | High | Architect | Open
V-20 | Where the SAP document persists an external request identifier, per document type. | Design decision informed by inspection | NFR-01, all commands | High | ABAP | Open
V-21 | Is batch management active for all relevant materials? Does shelf life apply? | Master-data inspection | API-04, API-03 | Medium | MM | Open
V-22 | Which invoice identifier the portal requires at each point - billing document, IRN, accounting document, or display number. | Functional confirmation | API-07, API-08, API-06 | Medium | SD / FI | Open
V-23 | Standard authorization objects in force, and whether existing depot roles already scope by plant. | Authorization inspection | NFR-05, all | Medium | Basis / Security | Open
V-24 | Where statutory and invoice output documents are stored and how they are retrieved. | Configuration inspection | Portal download requirement | Medium | SD / Tax | Open
V-25 | Is Modify DI in scope? It is absent from the client process register but Create DI has no amend path without it. | Scope confirmation | API-10 | Medium | Client / SD | Open
V-26 | Transporter and vehicle master exist in both Commerce T2 and Datasphere. Which is authoritative, and which value does SAP receive at posting? | Architecture decision | API-03, API-05, API-06, API-10 | High | Architect / Commerce / DSP | Open
V-27 | Mapping from Commerce depot, storage location, depot-SL and SL-SPI codes to SAP plant and storage-location values. Who owns the mapping and where does it execute - Commerce, CPI or SAP? | Architecture decision | API-01 to API-06, API-10 | Critical | Architect / SD / Commerce | Open
V-28 | Datasphere carries an e-invoice object of unconfirmed source. Does it duplicate the SAP e-document status, and which does the portal read? | Lineage inspection | API-08, API-06 | Medium | Datasphere / Tax | Open
V-29 | What does SAP push to Commerce T1 for the pending-order, deliveries and invoice-billing views, on what trigger and at what latency? Existing flow or new scope? | Architecture confirmation | Boundary of API-01; portal dashboard | High | Architect / CPI / Commerce | Open
NOTE | V-01, V-02, V-06, V-15, V-16, V-21 and V-23 are answerable within the first two days of development access and together resolve the classification of six of the ten APIs. V-26 to V-29 arise from the client landscape diagram and are cross-system decisions, not ABAP decisions.

## Source of Record
SOURCE OF RECORD - CROSS-SYSTEM MODEL
S/4HANA is not the sole source of data for this product. It is authoritative for the business documents it creates and posts. Substantial master and operational data is owned by SAP Commerce Cloud, and analytical, consolidated and replicated data by SAP Datasphere.
Concept | Owning system | Currency | Note
Goods receipt, delivery, goods issue, shipment, shipment cost, billing document | S/4HANA | Real time | Created and posted in SAP. Authoritative document numbers
Stock and batch availability | S/4HANA | Real time | Transactional decision - must not be served from a replicated snapshot
IRN and E-Way Bill | Statutory portal, persisted in S/4HANA | Real time | Datasphere also carries an e-invoice object of unconfirmed source - V-28
Pending order list, deliveries, invoice billing as shown in the portal | Commerce T1 | Pushed from SAP via CPI | The storefront reads these from Commerce over OCC, not from SAP directly - V-29
Invoice download | Commerce T1, CRM portal fallback | - | SAP is not the primary retrieval path for the document file
Depot, user, agent-depot, geography master, material alias, Incoterms, storage location, depot-SL, SL-SPI | Commerce T2 | Commerce-maintained | Portal master data. Not SAP-sourced. Mapping to SAP organisational values must be defined and owned - V-27
Vehicle master, transporter | Commerce T2 AND Datasphere | Daily refresh in DSP | DUPLICATED. Ownership must be resolved - V-26
STO, MRN | Datasphere | Near real time | MRN is NOT generated by SAP in this architecture. API-02 must not derive it - V-09
plant-SL, ageing report | Datasphere | Daily refresh | Analytical and reference reads
CONSEQUENCES FOR THE SAP SCOPE
1. MRN is a Datasphere object, not a SAP output | Earlier technical material derived the receipt note reference inside the goods-receipt function by prefixing the material document number. That is incorrect under this architecture. SAP returns the material document key; MRN resolves in its owning system.
2. API-01 is narrower than a general pending-order read | The portal pending-order list is served from Commerce T1. API-01 covers the SAP-side receipt position, which is a different question from what the dashboard displays.
3. Storage location, depot-SL and SL-SPI originate in Commerce T2 | They are inputs to the SAP APIs, not values SAP derives. The Commerce-to-SAP organisational mapping must be defined and owned.
4. Transporter and vehicle master are duplicated | Present in both Commerce T2 and Datasphere. Which is authoritative, and which value SAP receives at posting, is unresolved.
ARCHITECTURE CONFIRMED | SAP Integration Suite sits in the runtime path between Commerce Cloud and S/4HANA. Earlier material showed a direct storefront-to-Gateway connection with no middleware; that reading is superseded. What remains open is whether the integration layer or ABAP owns the outbound statutory calls and their credentials - V-03.

## Assumptions
ASSUMPTION LOG
Ref | Assumption | Impact if wrong | Confidence
A-01 | SAP Integration Suite sits between Commerce Cloud and S/4HANA and owns transport retry | - | CONFIRMED by client architecture diagram
A-02 | For the documents it creates, S/4HANA is authoritative for validity, posting, locking and numbering. It is NOT the source of record for Commerce- or Datasphere-owned concepts | Validation would need to move layer | High
A-03 | DI is the outbound delivery; DI number is the delivery number | Delivery-related APIs change object | Confirmed by client team
A-04 | One storage location per dispatch, multiple batches within it | Allocation model and API-04 response shape change | Medium
A-05 | The dispatch-to-invoice sequence spans multiple SAP units of work | If atomic, API-06 redesigns entirely | High on engineering grounds; requires functional confirmation
A-06 | Classic shipment (VT01N) and shipment costing (VI01) are in use | - | CONFIRMED - SRC-DOC-20260803-01 sec 3.3
A-07 | SAP Document Compliance for India is licensed and handles IRN and E-Way Bill | API-08/09 reclassify; E-Way extension may leave ABAP scope entirely | CONTRADICTED 2026-08-03 - client uses DigiGST (/DIGIGST/INVP), NOT SAP DRC. E-Way extension stated as 'not core SAP'. See D-017, Q-042
A-08 | Batch management is active for dispatched materials | API-04 response shape simplifies | Medium
A-09 | Modify DI is required even though absent from the client register | If out of scope, API-10 is removed and Create DI has no amend path | Proposed - see V-25
A-10 | Commerce T2 masters (depot, storage location, depot-SL, SL-SPI, Incoterms, material alias) are inputs to the SAP APIs, not SAP-derived values | Mapping ownership and derivation move into SAP scope | Confirmed by client architecture - mapping owner open, V-27
A-11 | MRN, STO, plant-SL and ageing are Datasphere-owned; SAP does not generate MRN | API-02 would need an MRN derivation rule and an owner | Confirmed by client architecture - V-09
A-12 | Architecture Option C selected: Orders/Deliveries/Invoices live from Hybris T1; MRN/STO/Ageing and masters synced DSP to T2 | Most read APIs leave SAP scope; an unowned S/4 to T1 push appears | Relayed by Siddharth 2026-08-03 - deck presents options neutrally, selection not marked in the document. See D-014
A-13 | Brand=MVGR3, Grade=MVGR2, Trade/NonTrade=MVGR5 - plain material group fields, not classification characteristics | Response shape and joins simplify substantially | DOCUMENTED - SRC-DOC-20260803-02. Supersedes the class-type-022 hypothesis