## Timeline
C&F AGENT INTERFACE - SAP DELIVERY TIMELINE
Sr | Phase | Activity | Start Date | End Date | Days | Status
1 | Preparation | Data briefing and landscape walkthrough | 25-Jul-2026 | 27-Jul-2026 | 2 | Complete
2 | Preparation | Structural reasoning and solution architecture | 27-Jul-2026 | 28-Jul-2026 | 2 | Complete
3 | Preparation | Requirement gathering and functional sign-off | 28-Jul-2026 | 29-Jul-2026 | 2 | Complete
4 | Preparation | Technical documentation and specification | 29-Jul-2026 | 30-Jul-2026 | 2 | Complete
5 | Milestone | DEV access received (window 31-Jul to 05-Aug) | 03-Aug-2026 | 03-Aug-2026 | 0 | Pending
6 | Build | Shared framework and foundations | 03-Aug-2026 | 12-Aug-2026 | 8 | Planned
7 | Build | API-04 Stock Availability | 07-Aug-2026 | 18-Aug-2026 | 8 | Planned
8 | Build | API-10 Modify DI | 11-Aug-2026 | 14-Aug-2026 | 4 | Planned
9 | Build | API-05 Shipment Cost | 13-Aug-2026 | 26-Aug-2026 | 10 | Planned
10 | Build | API-03 Create DI | 17-Aug-2026 | 24-Aug-2026 | 6 | Planned
11 | Build | API-01 Check MIGO | 18-Aug-2026 | 27-Aug-2026 | 8 | Planned
12 | Build | API-07 Invoice Correction | 25-Aug-2026 | 31-Aug-2026 | 5 | Planned
13 | Build | API-06 Invoice Creation | 26-Aug-2026 | 08-Sep-2026 | 10 | Planned
14 | Build | API-02 Submit MIGO | 28-Aug-2026 | 03-Sep-2026 | 5 | Planned
15 | Build | API-08 E-Invoice Correction | 01-Sep-2026 | 07-Sep-2026 | 5 | Planned
16 | Build | API-09 E-Way Bill Extension | 08-Sep-2026 | 11-Sep-2026 | 4 | Planned
17 | Testing | Unit testing (UT) | 01-Sep-2026 | 14-Sep-2026 | 10 | Planned
18 | Testing | System integration testing (SIT) | 17-Sep-2026 | 28-Sep-2026 | 8 | Planned
19 | Testing | User acceptance testing (UAT) | 29-Sep-2026 | 08-Oct-2026 | 8 | Planned
20 | Testing | Regression testing and defect closure | 09-Oct-2026 | 14-Oct-2026 | 4 | Planned
21 | Deployment | Cutover and go-live | 15-Oct-2026 | 16-Oct-2026 | 2 | Planned
22 | Deployment | Hypercare and post go-live support | 19-Oct-2026 | 23-Oct-2026 | 5 | Planned
| PHASE SUMMARY | Activity | Start Date | End Date | Days
| Preparation | All preparation activities | 25-Jul-2026 | 30-Jul-2026 | 4 | Complete
| Build | Framework and all ten APIs | 03-Aug-2026 | 11-Sep-2026 | 30 | Planned
| Testing | UT, SIT, UAT and regression | 01-Sep-2026 | 14-Oct-2026 | 32 | Planned
| Deployment | Cutover, go-live and hypercare | 15-Oct-2026 | 23-Oct-2026 | 7 | Planned
| TOTAL | Project start to go-live complete | 25-Jul-2026 | 23-Oct-2026 | 65
Working days only. Weekends excluded; public holidays not deducted.
Build start is dependent on DEV access. Any slip in access moves all subsequent dates equally.